## WBS
WBS ID | Task Name | Description
1.0 | Sports Jerseys Online Store Project | Overall project management and delivery
1.1 | Project Management | Planning, coordination, and reporting
1.1.1 | Project Planning | Define scope, schedule, and resources
1.1.2 | Progress Monitoring | Track tasks and milestones
1.2 | Requirements Analysis | Collect and validate requirements
1.2.1 | Business Requirements | Define business needs and goals
1.2.2 | User Requirements | Define customer website requirements
1.3 | Website Design | Design website structure and UI
1.3.1 | Website Layout Design | Define pages and navigation
1.3.2 | UI/UX Design | Design user-friendly interface
1.4 | Platform Setup | Configure e-commerce platform
1.4.1 | Platform Installation | Install and configure OpenCart
1.4.2 | Database Configuration | Setup database and data structure
1.5 | Product Management Setup | Configure product catalog
1.5.1 | Categories Setup | Setup teams and leagues
1.5.2 | Product Listing | Add jerseys, sizes, prices
1.6 | Payment & Shipping | Configure payment and shipping
1.6.1 | Payment Gateway Setup | Setup online payments
1.6.2 | Shipping Configuration | Configure worldwide shipping
1.7 | Testing & QA | Verify system functionality
1.7.1 | Functional Testing | Test checkout, cart, products
1.7.2 | Usability Testing | Test ease of use
1.8 | Deployment & Closure | Final deployment and handover
1.8.1 | Website Deployment | Launch website
1.8.2 | Documentation & Closure | Final report and closure